## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
FUNd Team | 2241-swen-261-02-B FUNd Team
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a U-Fund Manager I want to log in as an admin so that I can access the admin specific functions that allow me to modify the application. | Given I am a registered Admin, when I log in I can see the needs and edit them
Given I am logged in as an admin I can add, remove and modify the needs in the needs cupboard
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
As a Helper I want to log in with my specific username so that my data is saved for my personal preferences. | Given the login information matches the database when I hit the login button then I can manage my profile.
Given there is text in the username and password fields when I hit the login button, the username and passwords are checked in the database.
As a Helper I want to see a list of needs so that I choose which ones to contribute to. | Given the cupboard has some needs when I open the website then all the needs in the cupboard should be displayed.
Given I see a need I am interested in when I click on that need then the user should see detailed information about the need, including a more comprehensive description, context, requirements, and estimated time or resources.
As a Helper I want to search for specific needs so that I can find the needs I have a personal interest in. | Given the cupboard has needs when I search for a certain name or location then I should see a display of needs with matching criteria to the terms I searched.
As a U-Fund Manager I want to be able to add needs to the cupboard so that I can keep the list of needs updated for new needs. | Given I have a new need when I want to add that need to the cupboard then the need can be added to the cupboard through an easy-to-use system.
Given I add a new need to the cupboard when I look through the cupboard then the new need I just added should also be listed there.
As a U-Fund Manager I want to be able to remove needs from the cupboard so that I can remove old needs that are no longer applicable/viable. | Given I am logged in as a manager when I select a need, I should be able to remove it.
Given I am logged in as an admin when I click the delete button, the need is removed
As a U-Fund Manager I want to be able to edit the needs in the needs cupboard so that I can make sure that all needs have current relevant information. | Given I am logged in as an admin, I can select a need to edit it
Given I am logged in as an admin, I can click the save button to update the needs cupboard with my changes
As a Helper I want the needs in my basket and the needs I have volunteered for to save server side so that I can leave the application and come back to the same needs basket and schedule. | Given I am logged in as a helper, when I log off the application and come back, my basket should have the same needs as when I left
Given I am a helper signed up for a need, when I log off the application and log back on again, I should still be registered to that need
As a Helper I want to add the needs to a basket to gather multiple needs at once to volunteer for. | Given I am logged as a helper, when I select a need, I can add that need to the basket
As a Helper I want to remove needs from my basket to that I don’t have to volunteer for a need that I have no real intention of volunteering for. | Given I have needs in my basket when I want to remove them then I should be able to remove them from my basket.
Given I want to remove needs from my basket when I click the minus sign on a need then it should be removed from my basket.
As a Helper I want to “check out” my needs basket so that my spot as a volunteer is reserved. | Given I have needs in my needs basket when I want to reserve my spot as a volunteer for a need then I can check out the needs I have in my basket.
As a Helper I want to be able to see a list of the needs I’ve scheduled and their times so that I can see what I’ve volunteered for and their times. | Given I am a helper, when I log in, then a list of tasks appears in my dashboad
Given I am a helper, logged in, when I click on a task, then I can see the task details and where to sign up for it
As a Helper I want to be able to “refund” certain needs if I can no longer complete them so that I do not offer help that I cannot give. | Given I have checked out some number of needs when I do not want to volunteer for those needs anymore for whatever reason then I should be able to back out from volunteering for that need.
Given I have refunded a need when I look at the list of needs I have agreed to volunteer for then I should not see the need I refunded.
Given I am a helper on a need, when I push the refund button then I want to be removed from that need.
As a U-Fund Manager I want to be able to see a list of times for needs for a facility so that I can manage the organization’s volunteer schedule. | Given facilities have needs assigned when look at the list of needs then they should be sorted by facility.
As a Helper I want to have a profile saved to my username so that I can change preferences and see personal data attached to my profile. | Given I have logged into my account And my user information and profile are present When I navigate to my dashboard Then I should be able to view my profile as the U Fund manager sees it
Given I have logged into my account When I edit my profile information And I save the changes Then the database should be updated with the correct information
As a U-Fund Manager I want to be able to access/receive Helper contact information so that I can contact them when they volunteer for needs | Given I am logged in as admin when a Helper checks out a needs then I should be able to access their contact information.